## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen-610-01-3-team3
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | RJ; 10/3/2021;PASS PW;10/5/2021;PASS
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | RJ; 10/3/2021;PASS PW;10/5/2021;PASS
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | RJ; 10/3/2021;PASS PW;10/5/2021;PASS
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | PW;10/5/2021;PASS
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | PW;10/5/2021;PASS
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | PW;10/5/2021;PASS
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | PW;10/5/2021;PASS
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | PW;10/3/2021;FAIL - Update does not happen, you have to click on the players name that selected you to get into the game page. PW;10/5/2021;PASS
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | PW;10/3/2021;PASS - square lights up and allows it to drop, but the Ajax call to do so has not been implemented. This is expected as piece movement has not been implemented. PW;10/5/2021;PASS
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | PW;10/3/2021;PASS PW;10/5/2021;PASS
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I am a signed in player, when I click the sign out link, I should be signed out and redirected to the home page |  | PW;10/5/2021;PASS
As a Player I want to view whose turn it is so that I know when I can move my checker pieces. | Given that I am a player playing a game, I should see a string of text at the top of the screen indicating which player's turn it is. |  |  |  | PW;10/31/2021;PASS
As a Player I want to be able to upgrade my checker piece to a king so that I can take advantage of the forward and backwards motions as well as jumps it provides that checker piece. | As a player playing a game if I reach the end of the board as a normal piece, my piece should become a king |  |  |  | PW;10/31/2021;PASS
As a Player I want to be able to see the result of my own moves as well as my opponents moves so that I understand the current state of the game. | Given that I am a active player when either player takes their turn then I should be able to see the moves that have been made. |  |  |  | PW;10/31/2021;PASS
As a Player I want to drag my checker pieces to an adjacent dark square away from me so that I can advance them towards my opponent’s king row. | 'Given' that I want to make a move when I move 1 square diagonally then I expect the piece to move to that Place. |  |  |  | PW;10/31/2021;PASS
| Given that it is the opponent's turn when I try to make a move then I cannot make a move. |  |  |  | PW;10/31/2021;PASS
| Given that my piece is adjacent to an opponent's piece when I move the piece towards the opponent's piece then I expect to be able to move to a vacant space diagonally behind the opponent's piece. |  |  |  | PW;10/31/2021;PASS
| Given that I want to make a move when I move the piece backwards diagonally then the piece is not droppable. |  |  |  | PW;10/31/2021;PASS
As a Player I want to jump over my opponent’s checker piece with my checker piece to an adjacent square so that I can capture that checker piece. | Given that I am a Player playing the game, if my opponent's piece is directly diagonal to my piece, it is my turn, and there are no pieces directly behind the opponent's piece diagonally, if I click 2 spaces away diagonally, I should be able to jump over the opponent's piece and capture it. |  |  |  | PW;10/31/2021;PASS
| Given that my piece jumps over the opponent's piece when I capture the opponent's piece then the captured piece disappears from the board |  |  |  | PW;10/31/2021;PASS
As a Player I want to capture my opponents checker piece so that their checker piece is removed from the checkerboard and is unusable. | Given that I captured an opponent's piece and there are more available pieces to capture diagonally behind this piece when I move the same piece backwards to capture then my piece is not droppable. |  |  |  | PW;10/31/2021;PASS
| Given that I captured an opponent's piece there are more available pieces to capture when I move the same piece again to capture then I capture an additional opponent's piece. |  |  |  | PW;10/31/2021;PASS
As a Player I want to be able to resign/forfeit the game so that I can admit defeat early without having to play the rest of the game. | Given that I am a signed in player playing a game, if I click the "forfeit" button, I should be redirected to the home page (but still signed in)
Given that I am a signed in player and have forfeited, a message should be shown to me for 5 seconds that I have forfeited
Given that I am a signed in player playing a game, if my opponent forfeits, I should be redirected to the home page (but still signed in)
Given that I am a signed in player whose opponent has forfeited, a message should be shown to me for 5 seconds that my opponent has forfeited.
As a Player I want to be able to perform multiple jump moves chained together in one turn so that I can capture multiple checker pieces from my opponent at the same time. | Given that it is my turn in the game when I perform a jump with one of my pieces then I must not have my turn end if the result of the jump leads to the ability to perform another jump.
Given that it is my turn in the game when I perform a jump with one of my pieces then I should be notified that my turn has not ended and that I need to perform another jump.
Given that it is my turn in the game when I perform a chained jump then I should be able to redo a jump in the chain if I move my piece to a non-droppable space.
Given that it is my turn in the game and I am moving a king piece when I perform a chained jump then I should be able to chain jumps both towards and away from my side of the board.
As a Spectator I want to be able to join a game being played by two other players so that I can observe what is going on. | Given that I am signed-in when I click on a designated spectate button next to a player who is in a game then I should be brought to the game page associated with those players.
Given that I am signed-in when I click on a designated spectate button next to a player who is not in a game then I should be brought back to the home screen.
As a Spectator I want to be able to see every move made by both players so that I know the decisions made by each player during their turn. [NOT FINISHED] | Given that I am in an active game when either player makes a valid move then I expect to see the piece moved onto the new square.
Given that I am in an active game when either player captures an opponent piece then I expect to see the captured piece removed from the board.
Given that I am in an active game when either player makes a valid chained move then I expect to see each part of the move without it being "fast-forwarded" to the end.
Given that I am in an active game when either player forfeits the game then I expect to be notified that the game has been ended by a player prematurely.
Given that I am in an active game when a player wins then I should be returned to the home page.
As a Spectator I want to be able to leave a game at any time so that I do not have to watch it until the end. [NOT FINISHED] | Given that I am signed-in and spectating a game when I click on the exit button then I should be brought back to the home page.